## Summary
FDE 12-Week Plan: status update
Status date: 25 Oct 2026 ¦ Commitment: 18-20 hrs per week
Item | Value
Current week | Week 1: Role clarity and setup (all 4 tasks complete)
Overall status | Week 1 complete; 6 small follow-ups open before moving fully into Week 2
Tasks done | 4
Tasks in week | 4
Planned hours (Week 1) | 19
Hours counted as done | 19
Week 1 % complete | 100%
Hours remaining | 0
Next action | Close the Week 1 follow-ups (about 1 hr), then start Week 2: customer discovery, technical writing, enterprise data overview, Python part 2

## Week 1 Tasks
Week 1: Role clarity and setup - task tracker
Blue cells are the ones you edit (Status). Hours counted and totals recalculate. Status options: Done, In progress, Not started.
Task | Task name | Est. hrs | Status | Hours counted | Evidence / notes
1.1 | Understand the FDE role | 4 | Done | 4 | Palantir blog read; 5 JDs captured; recurring skills list written; one-page role map produced; role explanation drafted. Python and travel corrections now applied in your doc. Still outstanding: say the 2-minute explanation aloud (checkpoint).
1.2 | Dev environment (VS Code, Python 3.12+, Git, GitHub repo fde-journey) | 5 | Done | 5 | VS Code installed (v1.133.0); Python and Git working; GitHub account SushilB2402; repo fde-journey created with README and folders; first commits pushed from terminal; week1/hello.py written, run (prints Hello, world!) and pushed. GitHub commit list shows 3 commits: Initial commit, Add folder structure, Add hello world script. Minor: repo has notes/, projects/, resources/ instead of the journal/ folder in the checklist (fine; use notes/ for 1.4 or add journal/).
1.3 | Python basics, part 1 (CS50P lectures 0-2, 10 small scripts) | 7 | Done | 7 | 10 CS50P scripts written and run, each with output shown: indoor, playback, faces, einstein, tip, deep, extensions, math_interpreter, camel, twttr. Plus 2 checkpoint functions (is_even, hours-to-minutes = 210). See 1.3 Scripts tab. To confirm: all files committed and pushed to GitHub (no git log shown in doc); checkpoint1.py shows a stray duplicate print line in the doc.
1.4 | Start the learning journal | 3 | Done | 3 | Template (notes/journal-template.md), Week 01 entry with real blockers and fixes, and 5-bullet role summary all done. Open: friend checkpoint not possible (no friend available; wants to keep it private), so substitute a plain-English test; journal 'Next Step' needs aligning to Week 2; bullets still use some jargon.
| Total | 19 |  | 19 | 100% of planned Week 1 hours complete
Note: Est. hrs come from the 12-week checklist (Week 1 total 19 hrs). A task counts toward hours only when Status = Done.

## 1.1 Deliverables
Task 1.1: what you produced
# | Deliverable | Status | Notes
1 | Palantir blog post read | Done | Palantir Blog (Medium), 'A Day in the Life of a Palantir Forward Deployed Software Engineer', Nov 2, 2020, 7 min read.
2 | 5 FDE job descriptions captured | Done | Palantir, OpenAI (London), Anthropic (London), Databricks (London), Scale AI. Captured 19-20 Oct 2026.
3 | Recurring skills and responsibilities list | Done | Two corrections applied in your doc: Python (required or strongly preferred in 4 of 5; Palantir language-flexible) and travel (4 of 5; not Scale AI).
4 | One-page FDE role map (table) | Done | Five operational pillars: architecture and AI systems, production delivery, quality and evals, customer immersion, product feedback and reuse. Each has responsibilities, skills, customer scenario.
5 | Role explanation vs SWE, solutions engineer, consultant | Drafted | Written script exists. Checkpoint requires saying it aloud in about 2 minutes without notes.
6 | Bonus: 'A Day in the Life of a Forward Deployed Engineer' | Done (extra) | Third-party article; 75/15/10 time split (engineering / consulting and design / client relationship).

## 1.3 Scripts
Task 1.3: script review
# | Script | Problem set | Run evidence | Review notes
1 | indoor.py | PS0 Indoor Voice | Yes | Correct. Uses .lower().
2 | playback.py | PS0 Playback Speed | Yes | Correct. Uses .replace(' ', '...').
3 | faces.py | PS0 Making Faces | Yes | Correct; clean convert()/main() structure.
4 | einstein.py | PS0 Einstein | Yes | Correct for integer mass; E = m*c**2 with c = 300000000.
5 | tip.py | PS0 Tip Calculator | Yes | Correct; handles '$' and '%'. Calls main() without the __name__ guard used elsewhere; fix the comment typo 'afloat'.
6 | deep.py | PS1 Deep Thought | Yes | Correct; strip + lower and accepts 42 / forty-two / forty two.
7 | extensions.py | PS1 File Extensions | Yes | Correct; endswith with default application/octet-stream.
8 | math_interpreter.py | PS1 Math Interpreter | Yes | Correct for spaced input. Known limits (fine for the pset): '1+1' raises ValueError, unknown operator or divide by zero not handled.
9 | camel.py | PS2 camelCase | Yes | Correct; loop with isupper().
10 | twttr.py | PS2 Just setting up my twttr | Yes | Correct; omit_vowels() as a function. Strong use of a list and join.
11 | checkpoint1.py | Checkpoint: is_even(n) | Yes | Logic correct. The doc shows a duplicated 'print ... odd number' line after the else block; if it is in the file it causes an IndentationError, so confirm.
12 | checkpoint2.py | Checkpoint: hours to minutes | Yes | Correct: convert_hours_to_minutes(3, 30) returns 210.

## Fixes & Observations
Fixes before ticking 1.1 off, and observations
# | Type | Item | Detail / suggested change | Status
1 | Fix | Python is not a universal requirement | Skills list says Python is required across all 5 JDs. Palantir lists it as one option among Java, C++, TypeScript. Change to: 'required or strongly preferred in 4 of 5; Palantir is language-flexible.' | Done
2 | Fix | Travel appears in 4 of 5 JDs | Palantir, OpenAI, Anthropic and Databricks mention travel (25-50%). The Scale AI posting does not. | Done
3 | Checkpoint | Explain the role aloud, no notes | Record yourself once on your phone, about 2 minutes, covering what an FDE is and how it differs from a SWE, solutions engineer and consultant. | Open
4 | Observation | JDs split into two emphases | Scale and Anthropic lean toward LLM, agent and eval work. Palantir and Databricks lean toward data platforms and integration. The Week 5-8 projects cover both. | Info
5 | Observation | Experience bar and entry points | Most JDs ask for 4-5+ years of engineering experience. The Palantir posting saved is a US new-grad role requiring US clearance eligibility, so use it as a model of the role rather than a target. | Info
6 | Verify | Confirm 1.3 files are pushed | Doc shows run output but no git log for 1.3. Run 'git status' and 'git log --oneline', then check GitHub shows week1/cs50p/ with all 12 files and notes/ with the journal files. | Open
7 | Fix | checkpoint1.py stray line | A duplicated print line after the else block appears in the doc. Open the file and delete it if present. | Open
8 | Fix | Journal 'Next Step' does not match Week 2 | Entry says build CLI tools and learn API fundamentals. Week 2 is customer discovery (The Mom Test), technical writing, enterprise data overview, and CS50P part 2 (exceptions, libraries, file I/O). APIs come in Week 4. | Open
9 | Fix | Simplify the 5-bullet summary | Remove jargon for a non-technical reader: production-grade, backend, IT systems, system monitoring, core platform, startup CTO. Keep one everyday analogy. | Open
10 | Checkpoint | Friend test substitute | No friend available and you want to keep it private. Substitute: open a fresh Claude chat, say 'You are a non-technical reader', paste only the 5 bullets, ask it to explain the role back, and fix anything it gets wrong. | Open
11 | Observation | Strong Week 1 output | All 4 tasks delivered with evidence, 12 working scripts (2 beyond the 10 required), and a journal that records real errors and fixes, which is the habit the task is meant to build. | Info

## Next Steps
Next steps
Order | Action | Linked | Est. hrs | Timing
1 | Close Week 1 follow-ups: verify git push, fix checkpoint1.py, align journal Next Step, simplify 5 bullets, run the plain-English test in a fresh Claude chat; also say the 2-minute role explanation aloud | Week 1 | 1 | Before Week 2
2 | 2.1 Customer discovery: read The Mom Test; write discovery questions for a fictional hospital; role-play the call | Week 2 | 5 | Week 2
3 | 2.2 Clear technical writing: Google Technical Writing One; write a half-page status update | Week 2 | 4 | Week 2
4 | 2.3 Enterprise data and integration overview: Azure Data Fundamentals path; draw a CRM-to-report data-flow diagram | Week 2 | 5 | Week 2
5 | 2.4 Python basics, part 2: CS50P exceptions, libraries, file I/O; CSV cleaning script | Week 2 | 5 | Week 2
| Total hours (follow-ups plus Week 2) |  | 20